## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
WB | Episky and Kryptex latest TR shared | automation | Completed |  | 31/10/2017 | 9:15am | 10:50am | TR import completed at 10:50am
(BWS/BHS) | started Kryptex at | account | Completed |  | 31/10/2017 | 11:15am | 12:00pm | completed for BWS
| Waiting for the resource to work on BWS from account. (Episky) | account | completed |  | 31/10/2017 | 12:00pm | 4:46pm
| kryptex error for BHS | automation |  |  | 31/10/2017 | 2:16pm |  | load balancing during RFC creation(ABAP enhancements went on for a day)
| Episky for BWS started | account |  |  | 31/10/2017 | 5:30pm |  | started episky POT (template and kernel id generation TAB completed)
| mail sent from automation to account team for resuming the POT on BWS | automation | completed |  | 2017-02-11 | 10:52 | 10:52
| We got the reply | account | completed |  | 2017-02-11 | 10:54am | 10:54am
| Sent the mail for BWS is already latest kernel version and should be downgraded | automation | completed |  | 2017-02-11 | 3:05pm
| Kernel version for BWS was downgraded | account | completed |  | 2017-02-11 | 3:45pm
| Episky was started for BWS | account |  |  | 2017-02-11 | 3:50pm
| Error while copying the files after extracting the kernel files | automation | completed |  | 2017-02-11 | 4:00pm | 4:15pm | issue was fixed by automation team by 4:15
| the accounts team reverted back the system | account | completed |  | 2017-02-11 | 4:45pm | 5:30pm
| the soft link path specified in Kryptex was wrong | account | completed |  | 2017-02-11 | 5:30pm | 5:40pm | because of which icmdb permissions did not change
| Episky was complted on BWS | account | completed |  | 2017-02-11 | 5:45pm
| Got the verification mail for episky | account | completed |  | 2017-02-11 | 9:45pm
BHS | New TR for kryptex was sent | automation | completed |  | 2017-03-11 | 12:00pm | 12:18pm | TR was+J24 imported by 12:18pm( TR contained load balancing enhancement for RFC creation)
| No SUDO access for the given user for BHS | account |  |  | 2107-03-11 | 12:23pm
| team lunch |  |  |  | 2017-03-11 | 12:00pm | 3:00pm
| mail sent by automation team to resume POT on 6/11/2017 | automation | completed |  | 2017-03-11 | 5:44pm
| mail sent by automation to resume the POT | automation | completed |  | 2017-06-11 | 11:28am
| Reply for the mail from account team | account | completed |  | 2017-06-11 | 11:44am
| Kryptex started for BHS | account | completed |  | 2017-06-11 | 12:30pm
| load balancing enhancement issue and length soft link issue | automation | completed |  | 2017-06-11 | 1:00pm | 3:00pm | old TR was shared
| Kryptex started for BHS | account | completed |  | 2017-06-11 | 3:00pm
| Kryptex completed for BHS | account | completed |  | 2017-06-11 | 3:30pm
| Episky started for BHS | account |  |  | 2017-06-11 | 3:30pm
| Kernel ID issue | automation | completed |  | 2017-06-11 | 4:45pm | 5:00pm | Sequence was not correct for KID
| kernel upgrade failed because of no SUDO access on DB server | account |  |  | 2017-06-11 | 5:10pm
| Sudo access for DB server was provided | account | completed |  | 2017-07-11 | 9:33am
| Episky started | account | completed |  | 2017-07-11 | 3:47pm |  | Narasimha was Busy
| sudo access issue in CI server | account | completed |  | 2017-07-11 | 4:00pm
| Issue in start and stop of SAP | automation | incomplete |  | 2017-07-11 | 4:30pm |  | No instance profile to fetch the instance number.