## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
Fairfax | Episky package and Tr sent | automation | completed |  | 27/10/2017 | 11:59 |  | Account team was not available to finish the pre-requisite as they were occupied in town hall meeting
| Pre-requisite | account | completed |  | 27/10/2017 | 15:50 |  | Account team started with the pre-requisites
| Pre-requisite | account | completed |  | 27/10/2017 | 16:34 | 19:35 | Account team mailed saying permission issue while moving kernel files to "/usr/sap" 19:35 : Account team got the permission and placed the kernel files in /usr/sap
| availablity mail | automation | completed |  | 30/10/2017 | 10:31 | 10:34 | Automation team dropped a mail asking for the availability of the account team 10:34 : Account team replied saying Sunil is available 10:52 : Automation team had a Dstrum meeting 12:01pm : Automation team available after the meeting 12:13 : Account team started with POT
| Episky Execution |  | Started |  | 30/10/2017 | 13:55 |  | 13:55 : Application checks failed since the target(SBX) was down.
| Application/System checks | automation |  |  | 30/10/2017 | 14:47 | 15:46 | 14:47 : System checks failed - had to relaunch the tcode Application checks failed - rfc failed coz instance number was not passed properly.
| Db stop failed | automation | completed |  | 30/10/2017 | 16:06 | 16:43 | Db stop failed because of trailing space in the AL11 text file(input file) resulting in argument mismatch
| Kernel upgrade failed | automation |  |  | 30/10/2017 | 16:53 | 18:00 | Kernel upgrade failed due to timeout in script.
| Episky POT resumed |  |  |  | 31/10/2017 | 10:22 |  | Automation team dropped a mail asking for the availability of the account team 10:28 : Account team replied saying Sunil is available 10:45 : POT was resumed.
| Kernel upgrade failed | automation | completed |  | 31/10/2017 | 12:16 | 13:48 | 13:27 : Automation team found out that the proper permission for the /usr/sap folder was missing 13:48 : Account team resolved the issue.
| Kernel upgrade failed | automation | completed |  | 31/10/2017 |  | 17:30 | Modified kernel upgrade scripts had to be taken from WB system. When checked from the backend the database was not getting stopped as the online backup had been triggered for SBX, Automation team informed the same to account team. 20:37 : Account team dropped a mail saying the online backup was still in progress and we can resume the POT on 2/11/2017
| Episky POT resumed |  |  |  | 2017-02-11 | 9:33 |  | Automation team dropped a mail asking for the availability of the account team 9:43 : Account team replied regarding the availability 9:54 : Anwesh from account team started sharing the screen.
| Kernel upgrade failed | automation |  |  | 2017-02-11 | 10:10 |  | 12:23 : When checking the issue, automation team found that the scheduled online backup had been triggered which was causing the error. Automation team dropped a mail asking the Account team to cancel all the online backup for the day so that the testing and POT could be completed. 12:25 : Account team started working with the backup team regarding this issue 2:11 : Account team replied saying the online backup were disabled. 2:38 : Automation team dropped a mail saying that the POT would be resumed post lunch.
| Episky POT resumed | account |  |  | 2017-02-11 | 3:34 |  | 3:34 : Automation team dropped a mail asking for the availability. 3:37 : POT resumed. Account team executed from the beginning (for end to end execution) 4:25 : POT execution completed successfully and the account team dropped a mail regarding the same.