## Sheet1
Client | Date | Time | ABAPer | Scripter | Account Team | Issue | Status
MEDGEN |  |  | NIKITHA | PRAMODINI | SAI CHAITANYA TATIKONDA, VIJENDER VOORUKONDA
| 2017-07-19 | 4:30PM |  |  |  |  | PRE-REQ CHECKS COMPLETED
|  | 4:48PM |  |  |  |  | KRYPTEX TR SOLK900353 SENT TO THE CLIENT
| 2017-07-20 | 2:20PM |  |  |  |  | EPISKY TR SOLK900348 SENT TO THE CLIENT
|  | 5:00PM |  |  |  |  | KRYPTEX COMPLETED
|  | 5:20PM |  |  |  | UNONU AND ARCH WAS BLANK FOR CI | PERMISSION ISSUE RESOLVED
|  | 6:25PM |  |  |  | PASSWORD HAD @ | TICKET RAISED BY THE ACCOUNTS TEAM AND RESOLVED BY THEM
| 2017-07-21 | 10:00AM |  |  |  |  | EPISKY USER GUIDE BEING STUDIED BY THE ACCOUNTS PERSON
|  | 10:15AM |  |  |  |  | EPISKY POT STARTED FROM THE BEGINNING
|  | 10:30AM |  |  |  | DATABASE DEPENDENT KERNEL FILE ISSUE. ERROR - WIN62.py | THERE WAS A SPACE IN THE SAR FOLDER NAMING AND WAS RESOLVED
|  | 10:35AM |  |  |  | THE KERNEL FILES PREVIOUSLY DOWNLOADED WERE FOR A UNICODE SYSTEM AND ALSO, THE SAR FILES WERE UNCARRED | DOWNLOADING THE KERNEL FILES AGAIN BCOZ THE SYSTEM WAS NON-UNICODE
|  | 11:00AM |  |  |  |  | RE-EXECUTING EPISKY AGAIN
|  | 11:30AM |  |  |  | STEPS (3-9) (SCRIPTS) WERE SKIPPED | MISMATCH OF PARAMETERS PASSED
|  | 12:45PM |  |  |  |  | ISSUE RESOLVED BY THE AUTOMATION TEAM
|  | 1:10PM |  |  |  | R3 TRANS ISSUE - THE PASSWORD REQUIREMENT(@) WAS NOT UPDATED IN ONE OF THE SCRIPTS
|  | 1:27PM |  |  |  |  | ISSUE RESOLVED BY THE AUTOMATION TEAM
|  | 2:00-2:45PM |  |  |  |  | LUNCH BREAK
|  | 3:00PM |  |  |  |  | POT COMPLETED SUCCESSFULLY