## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
WB | pre-requisite check | accounts | completed |  | 2017-10-10 |  |  | architecture = abap is not maintained by accounts ,
| Kryptex | automation | completed |  | 2017-10-10 |  |  | combination is wrong- Ityp-text is not sent(ai,ci,db)
| Geminyo started | accounts/automation | completed |  | 2017-11-10 | 10:16 |  | Reached PSN at 10
| Geminyo Tr not imported | accounts | completed |  | 2017-11-10 | 10:20
| Error in 720 screen | automation | completed |  | 2017-11-10 | 10:32 | 10:51 | commented code for for getting the data file cofile
| Validation of template | accounts | delayed |  | 2017-11-10 | 10:56 | 1:51
| Geminyo scripts not sent to account team | automation | completed |  | 2017-11-10 | 11:00 | 11:58 | 11:29 - Scripts shared with account team 11:51 - 11:58 : Account team downloaded and placed the scripts in script location
| started with setup tab | accounts/automation | completed |  | 2017-11-10 | 13:57
| DIR_GEMINYO not maintained | accounts | completed |  | 2017-11-10 | 14:04
| BDLS mapping | accounts/automation | completed |  | 2017-11-10 | 14:13 | 14:40
| screenshot commented | automation | completed |  | 2017-11-10 | 14:53 |  | RDP
| import agent failed | automation | completed |  | 2017-11-10 | 15:20 | 18:45 | old wrapper and old script
| pre-refresh completed | accounts/automation | completed |  | 2017-11-10 | 22:48
| DB refresh | accounts | completed |  | 2017-11-10 | 22:49 | 2017-12-10 21:45
| post-refresh started | accounts/automation | completed |  | 13/10/2017 | 9:48
| Db refresh step re-occuring in actions tab inspite of submitting | automation | completed |  | 13/10/2017 | 9:49 | 10:24 | mismatch in the step description
| bg param script failed | automation | completed |  | 13/10/2017 | 10:06 | 11:27 | old wrapper , issue with the quotes
| sapparam failed | automation | completed |  | 13/10/2017 | 11:34 | 15:38 | issue with query(db2 first combination), issue with the quotes
| truncate table failed | automation | completed |  | 13/10/2017 | 15:40 | 16:15 | issue with quotes
| start failed | automation | completed |  | 13/10/2017 | 16:17 | 16:48 | aruguments missing
| system message failed | accounts | completed |  | 13/10/2017 | 17:06 |  | sap rfc not created as system msg step was manual
| license failed | automation | completed |  | 13/10/2017 | 19:35 | 16/10/2017 1:00 pm | issue with quotes, issue occurred after we left from psn, resumedand solved on 16/10/2017
| Waiting for citrix acess from account team | accounts | delayed |  | 16/10/2017 | 10:30 | 11:05
| POST step resumed | accounts/automation | completed |  | 16/10/2017 | 14:25 |  | mail sent at 1:00 pm account team responded saying they'll ping us soon at 1:12 POT resumed after lunch
| configuration of stms | accounts | completed |  | 16/10/2017 | 14:29 | 15:01
| import of E070L table | accounts | delayed |  | 16/10/2017 | 15:48 | 16:23
| restore of jobs failed | accounts | completed |  | 16/10/2017 | 16:32 | 16:48 | tsmadm rfc failed - accounts team fixed it
| manual step (STRUSTSSO2,STRUST,SECSTORE,SMQR/SMQS) | accounts | delayed |  | 16/10/2017 | 17:00 | 17:53
| smtp failed | accounts | delayed |  | 16/10/2017 | 19:00 | 23:30 | no space in log directory account team got into a call and decided to do it manually
| POST step resumed | accounts/automation | completed |  | 17/10/2017 | 10:12 |  | Mail sent at 9:19 response received at 9:20
| Waiting for account team |  | delayed |  | 17/10/2017 | 10:17 | 10:30
| login screen restore | accounts | delayed |  | 17/10/2017 | 10:30 | 11:09
| swu3 | accounts | delayed |  | 17/10/2017 | 11:09 | 11:20
| bdls | accounts/automation | completed |  | 17/10/2017 | 12:51 | 5:05 | import only from 000 n export also only in 000 (accounts - logical system name not maintained correctly in 000) Bdls entries not maintained correctly while taking snapshot in PRE
| Pot completed |  | completed |  | 17/10/2017 |  | 5:43