## Details
Details
Client Name | HMH
Solution | Geminyo
POT Start date : | 2017-05-08
POT End date : | 2017-09-08
Automation Resource : | Chaitra / Pramodini
Account Spoc: | Manu Susankar
Solution Spoc : | Koteshwer Pola

## Geminyo Sequence Status
Phase | Step | Type | Status
PRE REFRESH | PRE_CUA | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SM02 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_AL11 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_BD54 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_BD64 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_BTCOPTIONS | AUTOMATED | COMPLETED
PRE REFRESH | PRE_DB13 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_HTTPURLLOC | AUTOMATED | COMPLETED
PRE REFRESH | PRE_JOBS | AUTOMATED | COMPLETED
PRE REFRESH | PRE_OPMODE | AUTOMATED | COMPLETED
PRE REFRESH | PRE_PARTNER | AUTOMATED | COMPLETED
PRE REFRESH | PRE_PRINTER | AUTOMATED | COMPLETED
PRE REFRESH | PRE_RFC | AUTOMATED | COMPLETED
PRE REFRESH | PRE_RZ12SMLG | AUTOMATED | COMPLETED
PRE REFRESH | PRE_RZ70 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SAML2 | MANUAL | COMPLETED
PRE REFRESH | PRE_SDCCN | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SE06SCC4 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SICF | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SM69 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SMQRSMQS | MANUAL | COMPLETED
PRE REFRESH | PRE_SMTP | AUTOMATED | COMPLETED
PRE REFRESH | PRE_TLOCK | AUTOMATED | COMPLETED
PRE REFRESH | PRE_TPFET | AUTOMATED | COMPLETED
PRE REFRESH | PRE_USER | AUTOMATED | COMPLETED
PRE REFRESH | PRE_WE21 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_MONI | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SMQ1SMQ2 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_SE61 | AUTOMATED | COMPLETED
PRE REFRESH | PRE_STRUSTSSO2 | MANUAL | COMPLETED
PRE REFRESH | PRE_STRUST | MANUAL | COMPLETED
PRE REFRESH | PRE_LOGINIMAGE | MANUAL | COMPLETED
PRE REFRESH | PRE_SECSTORE | MANUAL | COMPLETED
PRE REFRESH | PRE_STOP | AUTOMATED | COMPLETED
PRE REFRESH | PRE_BGPARAM | AUTOMATED | COMPLETED
DB REFRESH | DB_1 | MANUAL | COMPLETED
DB REFRESH | DB_2 | MANUAL | COMPLETED
DB REFRESH | DB_3 | MANUAL | COMPLETED
POST REFRESH | POST_BGPARAM2 | AUTOMATED | COMPLETED
POST REFRESH | POST_SAPUSERPARAM | AUTOMATED | COMPLETED
POST REFRESH | POST_SAPSTART | AUTOMATED | COMPLETED
POST REFRESH | POST_LICENSE | AUTOMATED | COMPLETED
POST REFRESH | POST_STMS | MANUAL | COMPLETED
POST REFRESH | POST_IMPORTAGENT | AUTOMATED | COMPLETED
POST REFRESH | POST_CUA | AUTOMATED | COMPLETED
POST REFRESH | POST_MODIFYSE06 | AUTOMATED | COMPLETED
POST REFRESH | POST_RDDNEWPP | MANUAL | COMPLETED
POST REFRESH | POST_USER | AUTOMATED | COMPLETED
POST REFRESH | POST_CLEANUP | AUTOMATED | COMPLETED
POST REFRESH | POST_RFC | AUTOMATED | COMPLETED
POST REFRESH | POST_WE21 | AUTOMATED | COMPLETED
POST REFRESH | POST_PARTNER | AUTOMATED | COMPLETED
POST REFRESH | POST_SM69 | AUTOMATED | COMPLETED
POST REFRESH | POST_RZ12SMLG | AUTOMATED | COMPLETED
POST REFRESH | POST_JOBS | AUTOMATED | COMPLETED
POST REFRESH | POST_OPMODE | AUTOMATED | COMPLETED
POST REFRESH | POST_TPFET | AUTOMATED | COMPLETED
POST REFRESH | POST_BD54 | AUTOMATED | COMPLETED
POST REFRESH | POST_BD64 | AUTOMATED | COMPLETED
POST REFRESH | POST_SICF | AUTOMATED | COMPLETED
POST REFRESH | POST_DB13 | AUTOMATED | COMPLETED
POST REFRESH | POST_RZ70 | AUTOMATED | COMPLETED
POST REFRESH | POST_STRUSTSSO2 | MANUAL | COMPLETED
POST REFRESH | POST_STRUST | MANUAL | COMPLETED
POST REFRESH | POST_SECSTORE | MANUAL | COMPLETED
POST REFRESH | POST_SMQRSMQS | MANUAL | COMPLETED
POST REFRESH | POST_TLOCK | AUTOMATED | COMPLETED
POST REFRESH | POST_PRINTER | AUTOMATED | COMPLETED
POST REFRESH | POST_HTTPURLLOC | AUTOMATED | COMPLETED
POST REFRESH | POST_BTCOPTIONS | AUTOMATED | COMPLETED
POST REFRESH | POST_SDCCN | AUTOMATED | COMPLETED
POST REFRESH | POST_SMQ1SMQ2 | AUTOMATED | COMPLETED
POST REFRESH | POST_AL11 | AUTOMATED | COMPLETED
POST REFRESH | POST_MONI | AUTOMATED | COMPLETED
POST REFRESH | POST_SMTP | AUTOMATED | COMPLETED(000 ONLY)
POST REFRESH | POST_SE61 | AUTOMATED | COMPLETED
POST REFRESH | POST_LOGINIMAGE | MANUAL | COMPLETED
POST REFRESH | POST_SWU3 | MANUAL | COMPLETED
POST REFRESH | POST_SAML2 | MANUAL | COMPLETED
POST REFRESH | POST_ST03N | AUTOMATED | COMPLETED
POST REFRESH | POST_RZ10 | AUTOMATED | COMPLETED
POST REFRESH | POST_SICK | AUTOMATED | COMPLETED
POST REFRESH | POST_BDLS | AUTOMATED | COMPLETED
POST REFRESH | POST_HEALTH | AUTOMATED | COMPLETED
POST REFRESH | POST_BGPARAM3 | AUTOMATED | COMPLETED
POST REFRESH | POST_SE06SCC4 | AUTOMATED | COMPLETED
POST REFRESH | POST_SAPUSERRESET | AUTOMATED | COMPLETED
POST REFRESH | POST_RESTART | AUTOMATED | COMPLETED
POST REFRESH | POST_SCREEN | AUTOMATED | COMPLETED

## Episky Sequence Status
Step | Owner | Status

## Issue tracker
Phase | Step | Start date and time (dd/mm - hh:mm) | Status ( closed / open) | End date and time (dd/mm - hh:mm) | Issue Description | Solution Type( workaround / permanent) | Issue Owner | Actions Taken
KRYPTEX STARTED |  | 2017-08-05 | CLOSED | 2017-08-05 | # in the password (OS) | WORKAROUND | ACCOUNTS | Password was changed
|  | 8.47 AM |  | 10.30 AM | AIX and Ora combination wrong |  | ACCOUNTS
|  |  |  | 11.13 AM | error due to s01 file in kernel location instead of q01 |  | ACCOUNTS | Correct target-q01 kernel location was selected
|  |  |  | 3.00 pm | LMDB INCONSISTENCY | PERMANENT | ACCOUNTS | Programmatical changes were made - fixed
|  |  |  | 3.35 pm | KRYPTEX RESUMED-SUCCESSFULLY COMPLETED
GEMINYO STARTED | TEMPLATE CREATION | 3.35 pm | CLOSED |  | network issue and laptop so template had to be created thrice | WORKAROUND | ACCOUNTS | Template creation completed
[5 empty] | in template preview -radio button is taking of prev scroll | NOT FIXED | AUTOMATION | NOT FIXED
[5 empty] | too many radio buttons on - dump | NOT FIXED | AUTOMATION | NOT FIXED
| SETUP | 4.40 PM
PRE REFRESH |  | 17:00 |  |  | auto it failed cos code was commented in new TR | WORKAROUND | AUTOMATION | New TR Was sent with the correct package
[5 empty] | auto it failed to execute certain steps | WORKAROUND | AUTOMATION | Rerun from setup multiple times
[5 empty] | auto it failed due to password capture | WORKAROUND | AUTOMATION | Password was made to change by the accounts team
|  |  |  | 11.20 pm | auto it completed
|  |  |  | 11.30 pm | pre tlock step failed bt was successful in OS Level | WORKAROUND | AUTOMATION | Logs were changed since it was successful
[5 empty] | SET BACKGROUND WORK PROCESS PARAMETER TO 0 failed | WORKAROUND | AUTOMATION | Manually changed to 0
|  |  |  | 1.30 am | PREREFRESH SUCCESSFUL
POST REFRESH |  | 2017-08-07 |  | 12.30 pm | Sap start failed - truncate failed | WORKAROUND | AUTOMATION | Manually done by scripter
[5 empty] | License failed | WORKAROUND | ACCOUNTS | Correct license was selected by accounts and imported
TMSADM rfcs were not working
|  | 2017-08-08 |  | 11.30 am | tmsadm Absent | WORKAROUND | ACCOUNTS | STMS was configured by accounts
[5 empty] | USERS restoration failed - multiple times- Script error | WORKAROUND | AUTOMATION | Script changes were made
000 was hardcoded
[5 empty] | error in accessing of capdemoacct | WORKAROUND | ACCOUNTS | Permissions were given by Accounts
|  |  |  | 3.30 pm | JOBS failed - | WORKAROUND |  | Ran it in foreground
[5 empty] | SNAPSHOT RESTORATION OF BD64 failed - action tab | WORKAROUND | AUTOMATION | executed agin and ran successfully
SYNC OFF Parameter was maintained
|  |  |  | 10.25 pm | Restore moni failed bt showing pass status in scripts
|  | 2017-08-09 |  | 1.30 am | BDLS failed | WORKAROUND | AUTOMATION | bdls.sql missing in target
Database password changed
[5 empty] | bgparam set to original -failed | WORKAROUND | AUTOMATION | Manually changed to original value
[5 empty] | restart failed | WORKAROUND | AUTOMATION | old package- parameters sent from wrapper were wrong