## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
ALE | kryptex execution | Rashmi & Jesna | completed |  | 24/10 | 2.40 pm | 2.47 pm | Mail for starting the POT by automation team was sent at 11.54 am
| Geminyo started… | Rashmi & Jesna |  |  | 24/10
| Template create (steps addition) | Rashmi & Jesna | completed |  | 24/10 | 3.45pm | 4.45 pm | delay due to the queries by the account's team for each step
| bdls mapping screen | Rashmi & Jesna | delayed |  | 24/10 | 5pm | next morning | error : client no.was not taking properly...on scrolling up and down the values for changing ; new TR was made and sent at 10.20 am
| new TR was created with few enhancements | Shruti | completed |  | 25/10 |  |  | new TR was created and sent at 10.20 am
| New TR import | Chetan | completed |  | 25/10 | 10.20 am | 11.51 am
| kryptex re-execution | Rashmi & Jesna | completed |  | 25/10 | 12.20 pm | 12.40 pm | Error : when sbx was chosen as target system, it was giving dump. Issue fixed at 12.40 pm
| Geminyo re-execution… | Rashmi & Jesna |  |  | 25/10
| pre refresh steps | Rashmi & Jesna | completed |  | 25/10 | 1.25 pm | 1.28 pm | 1) two steps( instead of only one i.e PRE_CUA) were shown in actions tab...it was bcz of not doing clean up. so it was taking prvs refid also. 2) Stopped at PRE_charm step (added by account's team) before DB refresh ; account team had problems with the db restore
| DB Restore mail sent at : 11.52 am discussed over lync- 2pm | Chetan/Garima | completed |  | 27/10
| POST Refresh steps | Rashmi & Jesna |  |  | 27/10 | 2.48pm | 4.08 pm | delay from account side (bcz of queries)
x | Error in SAP Start system | Jesna | completed |  | 27/10 | 4.14 pm | 30/10 - 1.40 pm | lot of delay due to screen sharing…issue fixed on 30/10 - 1.40 pm Parameter missing in wrapper
| mail sent : 10.29 am | Chetan/Garima | completed |  | 30/10 | 11.45 am |  | 3.45pm - 4.05pm - performing the manual step
| error in Post_CUA with yellow status | account |  |  | 30/10 | 4.06pm | 4.18pm | accnt team skipped the step...said they will check on this later.
| error in POST_user step | account |  |  | 30/10 |  |  | (was working fine in 000 only)..sync parameter was not set…
| Resumed on 31/10 mail sent sent at :11.18 am response at : 11.25 am | account |  |  | 31/10 | 12.40 pm | 2.35 pm | few changes were made in stms config by accnt' team - step failed again
| Resumed on 2/11 mail sent sent at : 10.00 am |  |  |  | 2nd nov | 11.45 pm |  | post_user step failed again...tmssup authorisation in target 000 test was failing… -accnt's team checking with db team
| Resumed on 3/11 - .50 pm mail sent for start of POT-10.26 am ; response at : 10.32 am mail sent for team lunch info- 11.28 am mail for availablity- 3.43 pm ; response at 3.46pm | account |  |  | 3rd march | resumed at 3.30pm | till 4.20 pm (due to meetings) | error of post_user solved - accnt's team contacted db team and it was resolved...nothing from automation team --after 4.20…accnt's team busy with meetings
Resumed POT on 6/11 mail sent at : 9.38 am response at : 10.48 pm
| configuration of local stms and rddnewpp prgm step (manual step) | account |  |  | 6th nov | 12.38pm | 12.45pm
| error in 'smtp configuration' failed |  |  |  | 6th nov | 1.55pm | 2.12pm | error bcz of session timeout ; re-executed the step
| resumed pot post lunch |  |  |  | 6th nov | 3.20 pm | 16:00 | checking for bdls table…by accnt team
| BDLS step start: 6th nov , 6pm end: 7th nov , 5pm | completed
| resumed on 8th nov mail sent : 10.43 am response : 11.05 am (for 12.30 pm) |  |  |  | 8th nov | 12.40 pm | 12.45 pm | blank entries in monitor tab - 12.45 pm...post_healthcheck step's step text is missing in monitor <noted down>
[5 empty] | 8th nov | 1.28pm |  | issue : 020 client was not existing... (able to login to 000...->scc4 -> no clients were shown at 4.30 pm ; fixed at 4.45 pm no issues from automation team....the clients got populated ... <NOTED> issue : then bgparam issue...it was giving 0 instead of the original value. (at 4.45pm to 5) they made it manual for the time being and proceeded
| Resumed on 9th Nov MAIL SENT: 10.15 AM RESPONSE :11.40 AM | completed |  |  | 9th nov | 12.45 pm |  | error : at 12.50 pm--not able to login to sbx due to 'error in license check ' 12.50 pm - 1.15PM post_delmsg error : msg was not getting deleted...the system msg was there only the first time they opened the sbx...after that msg was not displayed...the msg was either not created properly.. @ 1.50 pm action taken : we proceeded with the further stpe by populating the action tab and skipping.. <NOTED> post_trigger screenshot failed - due to the resoultion issue... 2.00 - 2.10pm (had exectued the tool from some other laptopn which didnt hv the required resolution.
[5 empty] | 9th nov |  |  | POST_TRIGGERSCREENSHOT - it was not able to find the system (sbx) 2.10 - 2.31 RE-EXECUTED THE STEP - it worked
completed at 2.40 pm
generating the report 2.45 pm - error : audit report was not getting generated...asking for admin user and passwrd