## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
Cargill | Pre- checks | automation | pending |  | 13/11/2017 | 15:10 |  | 1. 15:15 - OS level scripts not called because there was an issue with the number of characters. 2. Issues at os level - ping had to be called with the full path, profile path was hardcoded later taken as an input, cat and ls command did not have permission so changed it to sudo bash , sudo access at solman command changed.
| Pre-checks | automation | completed |  | 14/11/2017 |  |  | 1. 10:15 - mail sent from automation team. 2. Though the os checks had passed, it was showing cross in the zlmdb_check - the number of characters were changed.
| Pre-checks |  | completed |  | 14/11/2017 | 13:20 | 13:59
| Kryptex | automation |  |  | 14/11/2017 | 13:59 |  | 1.issue: db type was not getting populated : 2 pm action taken : enabled the field to enter manually:2:05 pm 2. issue : db type and dbsid were not taken : 2:20 pm action taken : changes in the code done in their environment : 5:30 pm 3. issue : after clicking on check - it remained on the same screen : 5:45 pm action taken : Os level script failed because modification not reflected in encrypted script, ping had to be called with the full path, looping for CI/DB, dbuser changed from "hdbsid" to "sidadm"
| Kryptex | account | completed |  | 14/11/2017 | 22:20 |  | 1. DB host was hanged so couldn’t login to the DB server 10:45 pm - account team fixed the issue. 2. 10:50 pm - db user did not have sudo access action taken : Account team raised a ticket for the same.
| Kryptex |  | completed |  | 15/11/2017 | 11:05 | 16:47 | 11:05 am - Mail sent from automation team 12:43 pm - Response from account team Ticket resolved at 3.12 pm 4:40 pm - POT resumed 4:47 pm - Kryptex completed.
| Geminyo ( pre-refresh) |  |  |  | 15/11/2017 | 18:46 |  | 6:46 pm - Tr and OS package sent by automation team. 11:18 pm - TR imported by account team
| Geminyo (resumed) | automation |  |  | 16/11/2017 | 11:18 |  | 11:18 am - Started 11:31 am - Steps were not getting converted to automated/manual action taken - changes in code ( few lines were commented) - 12:20 pm
| Geminyo (resumed) | account/automation |  |  | 16/11/2017 | 12:40 |  | 12:20 pm - Resumed 2:58 pm - incorrect OTP (after proceed) action taken - DIR_GEMINYO not maintained ( the account team maintained it later) - 3:23 - 3:35 pm 3:40 pm - on proceed from OTP screen, system checks failed. Action taken - ping had to be called with full path, "suse linux" had to be changed to "suse_linux" - 4:06pm
| Geminyo |  |  |  | 16/11/2017 | 16:40 |  | 4:40 pm - auto it issue - zip folder couldn’t get downloaded to the server. Action taken - relaunced the tool again : ran successfully - 5:20 pm
| Geminyo (inject agent) | account |  |  | 16/11/2017 | 17:45 |  | 5:45 pm - inject agent failed 17/11/2017 9:50 am - Resumed issue - when adding to the buffer we got an error saying "illegal format detected" stms issue - authorisation test failed for tmsadm and tmssup rfc's. even while trying to import manually, it gave "error 200" .
| Geminyo(inject agent) |  |  |  | 17/11/2017 | 11:50 |  | 11:50 am - Automation team dropped a mail asking the account team to import without copying the cofiles again as the account team had dropped a mail saying they were able to import after copying the cofiles again onto the server.
| Geminyo (resumed) |  |  |  | 20/11/2017 | 13:04 |  | 1:04 pm - above issued solved. 1:50 - resumed POT.(after lunch)
| Geminyo (tlock) |  |  |  | 20/11/2017 | 14:34 |  | 2:34 pm - tlock failed - script missing action taken - missing script was added. - 2:40 pm
| Geminyo |  |  |  | 20/11/2017 | 14:50 |  | 2:50 pm - resumed (account team had gone for lunch)
| Geminyo (bgparam) |  |  |  | 20/11/2017 | 15:28 |  | 3:28 pm - bgparam failed action taken - script modified - 3:48 pm
| Geminyo (pre -refresh) |  | completed |  | 20/11/2017 | 15:50 |  | Pre-refresh completed.
| Geminyo(db-refresh) |  | completed |  | 23/11/2017 | 9:57 |  | Account team sent a mail regarding the completion of DB Refresh.
| Geminyo(post-refresh |  |  |  | 24/11/2017 | 10:34 |  | Post refresh started.
| Geminyo(sap*) |  |  |  | 24/11/2017 | 10:37 |  | POST_SAPUSERPARAM step failed hana db query was run for the first time. (at ABAP level Dbhostname,username,password passed, at os level - query modified) Solved at 5:20 pm Step failed again at 5:27 pm 8:53 pm - issue fixed and dropped a mail saying that the POT wil; be resumed on monday(as suggested by account team)
| Geminyo (post-refresh) |  |  |  | 27/11/2017 | 10:28 |  | 10:28 am - POT resumed 10:30 am - Password for cgauto changed by account team(password expired) 10:46 am - cleanupjob failed ( at os level - query modified, at abap level - db sid passed instead of appsid)
| Geminyo(stms) |  |  |  | 27/11/2017 | 11:20 |  | Account team configuring stms
| Geminyo(BDLS) |  |  |  | 27/11/2017 | 10:19pm |  | PEPCLNT000 AND PEPCLNT300 CLIENTS Were not maintained in bd54
| Geminyo(BDLS) |  |  |  | 30/11/2017 | 1:00pm |  | bdls for 300 canceled (run time error : DBSQL_SQL_ERROR) (error_Possibility: OS level user name passwords got changed and was not updated in Kryptex)
| Geminyo(BDLS) - retriggered |  | completed |  | 2017-04-12 | 3:25pm |  | completed in 27hrs
| Geminyo(Reset sap*) |  | completed |  | 2017-06-12 | 5:40pm |  | new os level password's had to be updated in kryptex. While fecthing the profile in Lin24 multiple profiles were taken. Changes were made in script accordingly
| Geminyo(Deltion of system message) |  |  |  | 2017-06-12 | 6:07pm |  | There was no system message set