## Sheet1
Client | Date | ABAPer | Scripter | Account Team | Status | time | Automation team | Error from accounts team | Status
CPG | 2017-07-05 | Chaihra | Surabhi | Ali/Sunil/Ashish/Lokesh/Rajashekhar | POT started | 5:30PM | correct TR was sent but was not imported by them | geminyo TR was not imported though it was completed acc to them /RFC not created though completed they said | Completed
| 2017-07-05 |  |  |  | kryptex | 5:35 PM | Authorization error/RFC error(# in the pwd) | #' was presentin the password which was later changed by account team | Completed
| 2017-07-05 |  |  |  | kryptex resumed | 7:30PM | completed |  | Completed
| 2017-07-05 |  |  |  | geminyo tool sys chk fail | 11:20PM | wrong password or username | wrong password or username was passed by account team | Completed
| 2017-07-05 |  |  |  | Entries completed before snapshot | 11:30PM | RFC Error since password was changed | RFC Error since password was changed | Completed
| 2017-07-05 |  |  |  | screenshots started | 11:45PM | Completed |  | Completed
| 2017-07-05 |  |  |  | AFTER SNAPSHOTS PREREFRESH STEPS | 12:00AM |  |  | Completed
| 2017-07-06 |  |  |  | pre-refresh error | 12:30AM | had to do manual login , Se61 manually done,discussion about BDLS | Confusion on logical names to be entered, se61 csreen login info wasn’t correctly maintained in tables | Completed
| 2017-07-06 |  |  |  | pre-refresh error | 1:00AM | os level log4erp error- solved | there was some changes in this module which was later replaced with the old one by Automation team | Completed
| 2017-07-06 |  |  |  | pre-refresh completed | 1:45AM | Completed |  | Completed
| 2017-07-06 |  |  |  | Db refresh | 1:45AM | Db refresh yet to start |  | Completed
| 2017-07-06 |  |  |  | geminyo tool started again | 12:00PM | since the 000 client was not selected last time | 000 client is mandatory | Completed
| 2017-07-06 |  |  |  | screenshots completed | 1:30PM | completed |  | Completed
| 2017-07-06 |  |  |  | resumed again after uploading of screen shots | 2:40PM | took time more than 30 mins | Server was slow to upload | Completed
| 2017-07-06 |  |  |  | pre-refresh steps taking place | 3:30PM | error in login image of target sym-manually done |  | Completed
| 2017-07-06 |  |  |  | pre-refresh completed | 4:00PM | completed |  | Completed
| 2017-07-06 |  |  |  | restore started | 9:10PM |  |  | Completed
| 2017-07-06 |  |  |  | restore completed and SAPINST done | 12:48PM | completed |  | Completed
| 2017-07-06 |  |  |  | delay because of os and ABAP issue | 1:00PM | sap* param error(wrong parameter order was passed)os-solved |  | Completed
| 2017-07-06 |  |  |  | post-refresh started | 11:15PM | error in license parameters (params error sent by abap) |  | Completed
| 2017-07-06 |  |  |  | lisence done and started again | 01:00AM |  |  | Completed
| 2017-07-07 |  |  |  | local stms + rddnewpp | 1:15AM |  | delay of 15mins by acccount team | Completed
| 2017-07-07 |  |  |  | started again | 1:32AM | we21 failed , extra line in actions from script - solved |  | Completed
| 2017-07-07 |  |  |  | SAP* param reset passed incorrectly | 3:43am | sap* problem - solved |  | Completed
| 2017-07-07 |  |  |  | POST done except BDLS and ACR | 5:50AM | continued next day |  | Completed
| 2017-07-07 |  |  |  | bdls manually done by cpg |  | bdls was running from other clients on 000 - code is changed | run bdls manually | Completed
| 2017-07-07 |  |  |  | post completed |  | Post refresh successful |  | Completed
2017-07-09