## Sheet1
Date | Steps | Owner | Issues | Solution | Start Time | End Time
14/12/2017 | Mail sent for TR | automation team |  |  | 3:55pm | 5:34pm
14/12/2017 | PRE-CHECKS | account team | delay : because account's team had not maintained the path in al11 |  | 5.40 PM
14/12/2017 | PRE-CHECKS | account team | Sudo-access issues | accoun team resolved it | 18:00
PRE-CHECKS completed on 14/12/2017 at 9.30 pm
15/12/2017 |  |  | Delay from the account's team (busy with their day to day acitvities) Not able to login into SMP till 2:30 pm
15/12/2017 | KRYPTEX | Automation team | script encrypted is not over written | wrp_001.py was renamed wrp_001 | 3:35pm | 16:19
KYPTEX COMPLETED ON 15/12/2017 AT 4:20 PM
15/12/2017 | New tr was given | Automation team | Screen was missing in the previous TR | New TR was created, the missing screen was included | 16:42 | 5:08pm
15/12/2017 | PRE-REFRESH | Account team | account team was not able to access the solman at 5.15 pm
18/12/2017 | PRE-REFRESH |  | issue : error in system checks after giving otp...'sapr3 error' due to Mimatch in the quotes in dblogin | The quote mismatch issue was fixed | 11:50 | 12.16 pm
18/12/2017 | PRE-REFRESH | Automation team | issue : pre_tlock failed due to file name mismatch | filename was renamed to the proper name (win14) | 13:30 | 1.40pm
18/12/2017 | PRE-REFRESH | Account team | Account team had fire drill activity at their office…at 3pm |  | 15:00
18/12/2017 | PRE-REFRESH | Account team | performing Manual Steps till 5.40 pm |  |  | 17:40
PRE-REFRESH COMPLETED ON 18/12/2017 AT 6PM
19/12/2017 | DB REFRESH | Account team |  |  | 13:56
19/12/2017 | DB REFRESH | Account team |  |  | 18:54
DB REFRESH COMPLETED ON 19/12/2017 AT 6.54 PM
20/12/2017 | POST REFRESH | Automation team | Certain scripts were tested before starting Post refresh |  | 10:00 | 12.30 pm
20/12/2017 | POST REFRESH | Account team | Import of tables took time |  | 12.:41 pm
20/12/2017 | POST REFRESH | Automation team | Issue : post_user job got cancelled after 5 (account's team busy with their work:4.30-5 pm)
21/12/2017 | POST REFRESH | Automation team | action taken : wrp014 was not placed | it was placed in their solman and step was re-executed at 11.20 am | 11.20 am
21/12/2017 | POST REFRESH | Account team | issue: post_jobs failed at 11.50 am ; due to login screen appearing while giving tcode stms | account team resolved it | 1:44pm | 1.50 pm
21/12/2017 | POST REFRESH | Account team |  |  | 3:26pm
21//12/2017 | BDLS started at 5.15 pm |  |  |  | 5:15pm
BDLS completed at 22/12/2017 at 8.25 pm : total time taken : 24hrs 35 min
26/12/2017 | POST REFRESH | Account team |  |  | 11.45 AM
26/12/2017 | POST REFRESH | Account team | STOP SAP IMPORT TABLES AND START SAP took time - > 12.26 pm - 2.05 pm
26/12/2017 | POST REFRESH | Account team
POST REFRESH completed at 3.50 pm
26/12/2017 | Analytics tab |  | system execution report generated...but couldnt open in excel since their system was not supporting excel.. Audit report couldn’t be generated bcz of admin right issues.
System refresh completed on 26/12/2017 at 4.14 pm