## Sheet1
Date | Issue List | Product | Owner | Solution | Start Time | End Time
12.11.17 | sudo access check for the solution manager sidadm failed. | Pre-Check | Account Team | The sudo access has not been provided. The same has been skipped. | 16:00 | 18:00
12.11.17 | Connectivity and sudo check in target has failed | Kryptex | Account Team | The new scripts did not overwrite the old scripts while placing in the binary location. | 17:40 | 18:00
12.12.17 | SID was not coming in drop down in Geminyo. | Kryptex | Automation Team/ Account Team | The entries were not saved in the Kryptex after the check has been done. | 10:30 | 10:40
12.12.17 | Screenshot has been done manually | Geminyo | Account Team | Because of Citrix, the tool was not able to idenntify the local desktop path. | 11:00 | 12:00
12.12.17 to 12.13.17 | DB RESTORE | NA | Account Team |  | 12:00 | 8:00
12.13.17 | Post Refresh Started | Geminyo |  |  | 10:35
12.13.17 | License Failed | Geminyo | Account Team | There was space in the License File name | 10:58 | 11:15
12.13.17 | Manual Step - STMS + RDDNEWPP | Geminyo | Account Team | Not able to schedule RDDNEWPP job. The job had to be scheduled with the DDIC user. | 11:16 | 12:30
12.13.17 | Pre_Cleanup Failed | Geminyo | Account / Automation Team | SP_TRANS_SYNC was not maintained. The TR was already present in the Buffer. | 12:38 | 13:18
12.13.17 | Post_User Failed | Geminyo | Account / Automation Team | The TR was already present in the Buffer of eb5 (STMS_IMPORT). | 13:47 | 13:51
12.13.17 | Post_RFC Failed | Geminyo | Account / Automation Team | The TR was already present in the Buffer. | 13:54 | 14:09
12.13.17 | Post_RFC Failed again | Geminyo | Account / Automation Team | The TR was already present in the Buffer. Buffer File content was removed. | 14:10 | 14:45
12.13.17 | Post Refresh Resumed | Geminyo |  |  | 15:40
12.13.17 | BDLS Step in Actions Tab for Manual confirmation | Geminyo |  |  | 16:29
12.13.17 | BDLS Step confirmed | Geminyo |  |  | 16:43
12.13.17 | BDLS Issue | Geminyo | Automation Team | BDLS job was getting finished in a few seconds
12.14.17 | BDLS Started | Geminyo |  |  | 12:50
12.14.17 | BDLS Finished | Geminyo |  |  |  | 14:03
12.14.17 | Post-BDLS Steps Started with | Geminyo |  |  | 14:41
12.14.17 | Reset SAP* Parameter Failed | Geminyo | Automation Team | Modified Script was not placed | 14:46 | 15:06
12.14.17 | Post Refresh Completed | Geminyo |  |  |  | 15:13