## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
WB | TR was shared with the account team for comenzo and kryptex | account | completed |  |  | 10:30 | 10:40
| os package sent(time wasted in discussion about dispatcher and diagnostic agent) | account | completed |  |  | 11:20 | 11:30
| zmdb_chk started | account | completed |  |  | 11:40 | 11:50
| kryptex started | account | completed |  |  | 12:00 | 12:10
| BH5 lmdb configuration error | account | completed |  |  | 12:50 | 12:57
| BDS completed kryptex | account | completed |  |  | 12:57 | 1:15
| comenzo started BDS | account | completed |  |  | 1:20 | 1:40
| BW5 kryptex completed | account | completed |  |  | 1:41 | 1:50
| sys_stat(error in system checks scripts encountered) | automation | completed |  |  | 1:50 | 2:25
| sys_stat / error solved | automation | In progress |  |  | 2:25
completed
In progress
yet to start