## Sheet1
Client | Issue Description
WB | DIR_GEMINYO not maintained
WB | tmsadm rfc is not configured
WB | log file full
WB | sudo access is revoked in between the POT execution.
WB | wrong BDLS mapping
PGC | Job got cancelled as the template was wrongly created.
PGC | Account Team was not having clear picture of the steps to be selected for System Refresh.
PGC | DIR_TRANS entry is not present in Instance Profile.
PGC | Background Job Restore failed because STMS was not configured.
PGC | BDLS got cancelled as due to temse inconsistency
PGC | resource does not respond for hours together
HMH | TMSADM rfcs were not working
HMH | tmsadm Absent
HMH | error in accessing of capdemoacct - Permission Issue
MEDGEN | Space in .SAR file name
MEDGEN | Provided wrong .SAR file (For Non Unicode system, Unicode kernels has been provided)
BAUER | STMS configured wrongly. TRANS DIR location was wrong.
BAUER | Pre Cleanup step failed due to missing configurations.
BAUER | User snapshot restore (Manual Step) failed so rfc authentication occurred.
BAUER | No Spool processes were not present in target system.
BAUER | Post Screenshot failed due to failure in manual
ALE | STMS configured wrongly due to which tmsadm rfc was not working
ALE | Wrong entry in SM59 (Z_RUN instead of ZRUN)
ALE | wrong db schema name given while filling up system information
ALE | BDLS mapping was given wrong
ALE | sap* user got locked because wrong password has been entered repeatedly.
ENECO | Currupted profile due to duplicate entries. So SAP did not start until the profile file has been corrected.
ENECO | STMS was configured properly
ENECO | RFC authentication failed.
ENECO | sybase Parameter was not set so SMTP snapshot restore has failed.
OTHER | Trans_DIR was not configured locally
OTHER | RDDNEWPP job was not running after configureing STMS
OTHER | LMDB was not configured properly
OTHER | Sudo access was not given properly
OTHER | LMDB host details was not maintained properly
OTHER | user home directory was not maintained properly
OTHER | Enogh space was not available in the target system for restoring the database
OTHER | Login image backup was not taken properly
OTHER | BTCOPTIONS table was not maintained properly
OTHER | Python packages was not installed properly
OTHER | Proper permission was not given to the script directory in solution manager
OTHER | Sharename was accessable with ip address but not with hostname

## Action
Client | Action | Owner | Status | Inputs Available | start date | Start time | End time | Comments
| environment readiness TR shared | Surabhi and Navneet | Completed |  | 2017-11-02 | 11:48PM | 12:42 | all the TRs were sent and Pre-requisite check list script was sent and placed in their system
Bauer | environment readiness execution | Surabhi and Navneet | Completed |  | 2017-11-02 | 1:25PM |  | LMDB issue(hostname) and stms was not configured
| environment readiness execution | account | incomplete | NO | 2017-11-02 | 2:00PM | 2017-11-06 | execution was performed with SAP* password . SAP username and password was not given
| environment readiness execution | account | incomplete |  | 2017-11-06 | 9:00 | 5:58PM | stms issue resolved and Backup restoration was going on for PR6 and TS6(on 6th nov they were taking backing)
| mail for execution | automation |  |  | 2017-11-07 | 11:10 |  | started with POT
| SAP USER CREATION CONFIRMATION | account |  |  | 2017-11-07 | 11:30 | 12:55 | The user is unable to create an rfc connection and is prompting for password again (will be fixed by account team)
| USER NOT LEGITIMATE |  |  |  | 2017-11-07 | 11:35
| part of environment check dir_trans was found to be shared | account |  |  | 2017-11-07 | 11:35 | 12:55:00 PM- 1:20 | DIR_TRANS must be local
| dir_trans was made local | account |  |  | 2017-11-07 | 1:12
| legitimate user was made | account |  |  | 2017-11-07 | 1:12
| enviroment readiness done | account |  |  | 2017-11-07 | 1:12
| dump during kryptex execution | automation |  |  | 2017-11-07 | 1:15
| dump solved by automation team | automation |  |  | 2017-11-07 | 1:16
| account team started with kryptex | account |  |  | 2017-11-07 | 1:22
| filling details in kryptex | account |  |  | 2017-11-07 | 1:25 | 1:45
| issue in kryptex came due to the presence of cs in instance type(central server) | automation |  |  | 2017-11-07 | 1:45 | 2:00
| Kryptex Execution | account | completed |  | 2017-11-07 |  | 2:00:00 AM - 3:20 | completed
| lunch | automation |  |  | 2017-11-07 | 2:10 | 3:15
| geminyo execution started | automation |  |  | 2017-11-07 | 3:15
| resolution and font for geminyo execution was not set as per the pre requisite | account |  |  | 2017-11-07 | 3:16 |  | account team dint do the pre-requisites
| template creation started | account |  |  | 2017-11-07 | 3:30 |  | dumps came from abap end (3:30-5:30)
| multiple radio buttons in preview screen(dumps) | automation |  |  | 2017-11-07 | 3:40
| multiple radio buttons issues solved | automation |  |  | 2017-11-07 | 4:30
| password decryption error in system and application checks | automation |  |  | 2017-11-07 | 5:45
| new tr IMPORT COMPLETED | automation |  |  | 2017-11-08 | 10:15
| STARTED WITH SETUP tab | account |  |  | 2017-11-08 | 10:41 |  | mail for execution
| LISENCE INSTALLATION from sap marketplace | account |  |  | 2017-11-08 | 10:50
| lisence uploaded in the setup tab | account |  |  | 2017-11-08 | 11:00
| auto it failed | automation |  |  | 2017-11-08 | 11:20
| wrong wrapper was kept for auto it | automation |  |  | 2017-11-08 | 11:20 |  | for mssq script s little different
| auto it issue was solved POT resumed | automation |  |  | 2017-11-08 | 1:10
| lunch | automation |  |  | 2017-11-08 | 2:00 | 3:00
| pre refresh completed and db refresh started | automation |  |  | 2017-11-08 | 3:00 |  | no update from account team regarding the completion of pre steps and db was started by account team without automation team signoff
| POT resumed after checking POSt refresh scripts | automation |  |  | 2017-11-09 | 10:53 |  | mail sent to resume the POT by automation team
| bgparam2 issue: the sapservicesmp with which the script s running dint have full permission | automation |  |  | 2017-11-09 | 11:54 |  | solved by surabhi(gave full permission to reflog)
| truncate table failed |  |  |  | 2017-11-09 | 12:40 |  | wrp was not kept and script had lil change for mssql login
| POSt lisence failed |  |  |  | 2017-11-09 | 2:47 |  | ker path wrong acc team gave wrong kernel path (2 hours)
| lisence issue soved |  |  |  | 2017-11-09 | 5:06 |  | Navneet gave proper kernel path from backend as we could not run kryptex again
| stms +rddnewpp | account |  |  |  | 5:11 | 5:50
| pre clean up/import agent |  |  |  | 2017-11-09 | 5:50 | 9:30 | dir_trans entry missing solved by accounts team
| pre clean up/import agent | account |  |  | 2017-11-10 | 9:30 | 12:25AM | TMSADM rfc and tmssup rfc authorization test failed. In tp system log the rddimpdb job was terminated abnormally. On further RnD we checked the logs in sm21 and found that the background default server group SAP_DEFAULT_BTC does not contain any active background servers.
| pre clean up/import agent | account |  |  | 2017-11-10 | 12:25AM | 7:35AM | issue solved by account team and sent a screenshot of tmsadm only.but tmssup was not fixed.
| inject agent/pre clean up | automation |  |  | 2017-11-10 | 9:30AM |  | tried executing script but since the tmssup rfc failed the authorization test the tr was not getting imported even manually. We again ran rddnewpp job and checked the tp system log and found out thyt the rddimpdp job was terminated abnormally. And in sm21 the issue still persisted.
| inject agent/pre clean up | automation |  |  | 2017-11-10 |  | 12:56PM | dropped a mail to accounts team to fix the same at 1:40 PM acc team ack
| inject agent/pre clean up | account |  |  | 2017-11-10 |  | 2:48PM | account team solved the issue and sent a mail
| lunch | automation |  |  | 2017-11-10 | 2:45PM | 3:40PM
| inject agent/pre clean up | automation |  |  | 2017-11-10 | 3:50 | 4:09 | automation team checked whether the issue is solved or not(tmssup authorization failed) after importing tp from backend (passed)
| inject agent/pre clean up | automation |  |  | 2017-11-10 | 4:25 | 4:50 | resumed with POT
| inject agent/pre clean up | account |  |  | 2017-11-10 | 4:55 | 5:05 | account team checking for CUA (should be active or not)
| BDLS | automation |  |  | 2017-11-10 | 9:00PM | 11:10PM | BDLS completion dint come in log and monitor tab(Shurti solved)
| sap* param reset | automation |  |  | 2017-11-10 | 11:12PM | 11:17PM | changed script was not encrypted bt after encrypting also this script was not called and it dint come in log and monitor as well.
| saprestart | automation |  |  | 2017-11-10 | 11:20PM | 12:15AM | parameters were not passed properly from ABAP(shruti solved)
| post screenshots | account |  |  | 2017-11-11 | 12:20AM | 12:48AM | font size was not correct
| POST refresh completion | automation |  |  | 2017-11-11 | 12:49AM | 1:00AM | POST refesh completed