## Sheet1
Client | Date | Time | ABAPer | Scripter | Account Team | Issue | Status | ACCOUNTS TEAM | AUTOMATION TEAM
Bauer | 2017-07-05 | 11:00AM - 12:00PM | Nikitha | Pramodini | Santosh Farkande, Pola Koteshwer, Naveen Kondoju | Validation Checks | Completed
|  | 11:28AM |  |  |  | KRYPTEX TR Sent | SOLK900327
|  | 12:35PM |  |  |  | KRYPTEX POT | Completed
|  | 12:37PM |  |  |  | GEMINYO POT | Started
|  | 1:00PM |  |  |  | GEMINYO POT REQUEST TO MAKE STANDARD STEPS MANUAL - WE21 AND USER-MASTER SNAPSHOT RESTORE | POT Stopped and mail sent by Koteshwer regarding the same
|  | 3:40PM |  |  |  | NEW TR FOR GEMINYO SENT | SOLK900334
|  | 4:45PM |  |  |  | GEMINYO POT STARTED WITH THE NEW TR
|  | 11:54PM |  |  |  | FAILED : RESTORE THE SOURCE BACKUP IN THE TARGET SYSTEM | TARGET TS6 HAD RAN OUT OF SPACE - ACCOUNTS TEAM | YES
| 2017-07-06 | 1:21AM |  |  |  | SPACE ISSUE RESOLVED BY THE ACCOUNTS TEAM |  | YES
|  | 9:05AM |  |  |  | BACKUP FILE PATH CHANGED IN THE BACKEND BY AUTOMATION TEAM AND ASKED THE ACCOUNTS TEAM TO RE-EXECUTE THE DB-RESTORE STEP
|  | 9:53AM |  |  |  | DB-RESTORE STEP RE-EXECUTED BY THE ACCOUNTS TEAM
|  | 12:27PM |  |  |  | DB RESTORE COMPLETED AND SAPINST RUN MANUALLY
|  | 1:29PM |  |  |  | SAPINST STARTED MANUALLY
|  | 2:46PM |  |  |  | SAPINST DONE
|  | 3:03PM |  |  |  | PRECLEANUP STEP FAILED | SCRIPTS - TRUNCATE TABLE AND BACKGROUND WORK PROCESS PARAMETER ISSUE |  | YES
|  | 11:42PM |  |  |  | ISSUE RESOLVED BY THE AUTOMATION TEAM
2017-07-07
|  | 7:44AM |  |  |  | ACCOUNTS TEAM PROCEEDED WITH THE MANUAL STEP - STMS CONFIGURATION+RDDNEWPP
|  | 9:00AM |  |  |  | COMPLETED WITH THE MANUAL STEP - STMS CONFIGURATION +RDDNEWPP
|  | 10:08AM |  |  |  | ISSUE WITH THE CONFIGURATION OF STMS - ENTRY FOR TRANSDIR MISSING IN THE PROFILE FILE - ACCOUNTS TEAM |  | YES
|  | 12:10PM |  |  |  | PRECLEANUP STEP FAILED | STEP FAILED DUE TO MISSING CONFIGURATION | YES
|  | 12:17PM |  |  |  | TRANSDIR STILL NOT MAINTAINED IN PROFILE FILE |  | YES
|  | 2:35PM |  |  |  | PRECLEANUP RE-EXECUTED BUT TAKING TOO MUCH TIME TO COMPLETE | BECAUSE RDDNEWPP WAS NOT RUN PROPERLY BY THE ACCOUNTS TEAM | YES
|  | 6:02PM |  |  |  | ACCOUNTS TEAM ISSUE WITH BACKGROUND JOB SERVER RESOLVED | BGPARAM STEP FAILED | YES
|  | 8:01PM |  |  |  | CUA INACTIVE - NOT MAINTAINED AS PART OF THE PRE-REQUISITES BY THE ACCOUNTS TEAM |  | YES
2017-07-08
|  | 10:13PM |  |  |  | BDLS RUN MANUALLY BY THE ACCOUNTS TEAM
2017-07-09
|  | 4:38PM |  |  |  | USER IN TARGET SYSTEM LOCKED | USER IMPORT WAS TAKEN MANUALLY BY THE ACCOUNTS TEAM ; DURING POST REFRESH, THE PRODUCTION USERS/PASSWORD WAS PRESENT IN THE SYSTEM. NOTIFIED ON MAIL TO CHANGE THE PASSWORD TO THE SAME, WHICH WAS GIVEN DURING KRYPTEX, DUE TO WHICH THE TOOL WAS NOT ABLE TO LOGIN TO THE TARGET HENCE, RFC AUTHORIZATION WAS GIVING AN ERROR | YES
|  | 4:44PM |  |  |  | USER UNLOCKED BY THE ACCOUNTS TEAM | PASSWORD FOR NKONDO HAD TO BE RESET TO THAT, ENTERED DURING THE KRYPTEX
|  | 5:07PM |  |  |  | AUTORIZATION TEST FAILED FROM SMP TO TS6(500 CLIENT) IN SM59 FOR NKONDO USER
|  | 6:30PM |  |  |  | SICK ISSUE IN TARGET SYSTEM | NO SPOOL PROCESSES WERE PRESENT IN THE SYSTEM - ACCOUNTS TEAM | YES
|  | 7:38PM |  |  |  | SICK ISSUE RESOLVED BY THE ACCOUNTS TEAM
|  | 10:50PM |  |  |  | THE CREDENTIALS WERE NOT ENTERED BY THE AUTOIT | NKONDO PASSWORD WAS NOT RESET TO INITIAL PASSWORD BY THE ACCOUNTS TEAM BECAUSE OF WHICH AUTOIT WAS NOT ABLE TO ENTER THE CREDENTIALS
|  | 11:00PM |  |  |  | POT COMPLETED